## Burn Down Chart
Project Title: Minesweeper CLC Milestone Release #: Sprint #: 1
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 10
| 1 | As a player I would like to register myself into the game | Create registration form for new players | Mark Pratt | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Create Database to store players | Mark Pratt | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | As a user I would like to have an ability to login to the site | Create a Login Page wher users can create username and passwords | Patrick Garcia | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Store users login information within a database | Patrick Garcia | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | As a player I would like the site to be secure so that my login information is safe | Add security to the site to protect user information | Patrick Garcia | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | As a player I want to save my game data and stats | Connect players game stats and data to the database | Mark Pratt | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | As a player I want to be able to see my stats displayed on the screen | Display game stats and results on screen | Patrick Garcia | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | As a player I want to be able to see my old stats | Retrieve stats stored in database | Mark Pratt | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 18 | 16.2 | 14.4 | 12.6 | 10.8 | 9 | 7.2 | 5.4 | 3.6 | 1.8 | -3.1086e-15
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18

## Back Log
Task | Hours
Store users login information within a database | 1 hrs
Retrieve stats stored in database | 1 hrs
Create registration form for new players | 2 hrs
Create Database to store players | 2 hrs
Connect players game stats and data to the database | 2 hrs
Display game stats and results on screen | 2 hrs
Create a Login Page wher users can create username and passwords | 4 hrs
Add security to the site to protect user information | 4 hrs

## Product Log
Desired Features
Register New Users
Login to Game Site
Make Site Secure
Save Game Stats in database
Display Game Stats
Retrieve Stats from database

## How To Use
Step 1 | Hold a Sprint Planning meeting on Day 1 of of your Sprint where you will complete or update your User Stories as well as (re)prioritize your User Stories in your Product Back Log (ideally this should be done for the next 3-4 Sprints)
Step 2 | Copy the User Stories you plan to complete for this Sprint into your Sprint Back Log
Step 3 | Copy the User Stories you plan to complete from your Sprint Back Log into Column C
Step 4 | Break the User Story into a series of step by step development tasks in Column D
Step 5 | Estimate the User Story (in 1, 2, 4 or 8 Effort Man Hours) in Column F and if the task is larger than 8 hours break the User Story into multiple User Stories
Step 6 | Assign the User Story to a single Team Member in Column E
Step 7 | Repeat steps 4-6 for each User Story that has been planned for this Sprint
Step 8 | At the end of each day each Team Member should update the effort hours that were worked on their User Story to burn their work down
Step 9 | After each Daily Standup each Team Member should review the Burn Down Chart to ensure your Sprint will be delivered on time